## Project
TOWN OF DEWEY BEACH
Project Actual and Projected Since Inception Thru 9/30/2026
Category | Notes | Actual | Projected/ Remaining | Total | Budget | Variance
State Grant 1 |  | 3000000 |  | 3000000 | 3000000 | 0
State Grant 2 |  | 1000000 |  | 1000000 | 1000000 | 0
Sussex County | c | 750000 | 750000 | 1500000 | 1500000 | 0
Original Allocation + Brown Advisory |  | 3613855.32 |  | 3613855.32 | 3613855.32 | 0
Total Monthly Allocations (50% Hotel Lodging Tax) |  | 900418.33 | 118750 | 1019168.33 | 1019168.33 | 0
Loan - Community Bank | b | 3000000 |  | 3000000 | 3000000 | 0
Wall / TH Donations | d | 437501 |  | 437501 | 0 | 437501
Brick Donations | a | 180750 | 120000 | 300750 | 0 | 300750
DEMA Grant |  | 69908 |  | 69908 | 0 | 69908
Motorola Credits |  | 35031.5 |  | 35031.5 | 0 | 35031.5
Interest Income |  | 187855.03 |  | 187855.03 | 0 | 187855.03
Total Funds |  | 13175319.18 | 988750 | 14164069.18 | 13133023.65 | 1031045.53
|  |  |  | 0 |  | 0
Design and Consultation
GMB - design and construction consultation |  | -573335.76 |  | -573335.76 | 560000 | -13335.76
Fisher Architecture - design bid |  | -7000 |  | -7000 | 0 | -7000
Code Solutions Inc (Dave Naples) |  | -41763.44 |  | -41763.44 | 130000 | 88236.56
Construction
Costello Construction | e | -8065185.02 | -2594341 | -10659526.02 | 10585000 | -74526.02
Demolition |  | -15300 |  | -15300 | 15000 | -300
Furniture |  | -114011.63 | -114011.63 | -228023.26 | 450000 | 221976.74
Dias (Commissioner Desk) |  | -28820 |  | -28820 | 0 | -28820
Town Hall Fence |  | -7941 | -7941 | -15882 | 0 | -15882
Permit Fees |  | -37620 |  | -37620 | 63000 | 25380
Technology
Advantech |  | -83750 | -251250 | -335000 | 475000 | 140000
Mid South |  | 0 | -49893.72 | -49893.72 | 0 | -49893.72
Think Secure Net |  | 0 | -21668.18 | -21668.18 | 0 | -21668.18
Digital Monitoring System - Advantech | f | -64100 |  | -64100 | 0 | -64100
Operational
Rental Expense - Parking Trailer |  | -25543.47 |  | -25543.47 | 0 | -25543.47
Misc. |  | 0 | -50000 | -50000 | 3000 | -47000
Interest Expense |  | -28589.17 |  | -28589.17 | 0 | -28589.17
Fundraising
Donor Wall |  | -11226.6 | -18773.4 | -30000 | 0 | -30000
Bricks |  | -12598 | -50125 | -62723 | 0 | -62723
Total Expenses |  | -9116784.09 | -3158003.93 | -12274788.02 | 12281000 | 6211.98 | 0
Remaining Balance | Grand Total | 4058535.09 | -2169253.93 | 1889281.16
Actual loan amount needed |  |  |  | 1110718.84
Notes
a) 1/3 of bricks have been sold leaving additional opportunity of $360,000
b) With completion of phase 1, on being converted from interest only to principle and interest.
c) Sussex County to deliver remaining $750,000 upon 50% completion of EMS Station
d) Donor's wishing to be on donor wall will have ability through Memorial Day 2027
e) Includes October Invoice for work performed in September
f) Expense covered by DEMA grant

## CSI
P.O. No. | Order Date Description | P.O. Total
V4000553 | 2023-08-25 | 804.38
V4000632 | 2023-09-21 | 390
V4000890 | 2023-12-08 | 1023.75
V4001017 | 2024-01-26 | 244.38
V4001113 | 2024-02-23 | 683.13
V4001205 | 2024-03-29 | 487.5
V5001452 | 2024-04-18 | 316.88
V5001820 | 2024-07-26 | 146.25
V5002130 | 2024-10-25 | 292.5
V5002212 | 2024-12-02 | 195
V5002262 | 2024-12-20 | 121.88
V5002328 | 2025-01-17 | 48.75
V5002363 | 2025-02-07 | 823.89
V6003168 | 2025-05-30 | 390
V6003266 | 2025-06-20 | 755.63
V6003350 | 2025-07-11 | 658.13
V6003437 | 2025-08-01 | 828.76
V6003490 | 2025-08-14 | 341.25
V6003559 | 2025-09-02 | 585
V6003581 | 2025-09-05 | 292.5
V6003618 | 2025-09-19 | 414.38
V6003697 | 2025-10-10 | 658.13
V6003765 | 2025-11-03 | 1608.77
V6003788 | 2025-11-07 | 316.88
V6003822 | 2025-11-21 | 901.88
V6003891 | 2025-12-12 | 1908.13
V6003959 | 2026-01-02 | 2284.38
V6003982 | 2026-01-09 | 1021.26
V6004042 | 2026-01-23 | 1720.01
V6004074 | 2026-02-06 | 1558.75
V6004107 | 2026-02-20 | 1585.63
V6004163 | 2026-03-06 | 940.63
V6004190 | 2026-03-19 | 1263.13
V7004292 | 2026-04-03 | 1397.5
V7004366 | 2026-04-24 | 1800.63
V7004397 | 2026-05-01 | 1263.13
27-00019 | 2026-05-30 | 1128.75
27-00020 | 2026-05-30 | 1209.38
27-00180 | 2026-06-05 | 1935.01
27-00398 | 2026-07-31 | 3789.38
27-00435 | 2026-08-14 | 1585.63
27-00516 | 2026-08-28 | 1182.5
27-00535 | 2026-09-11 | 860.01
41763.44

## Costello
P.O. No. | Order Date Description |  | P.O. Total
V6003260 | 2025-06-16 |  | 565434
V6003349 | 2025-07-11 |  | 138924
V6003489 | 2025-08-14 |  | 432627.12
V6003580 | 2025-09-05 |  | 286154.55
V6003732 | 2025-10-17 |  | 567612
V6003821 | 2025-11-21 |  | 730413.63
V6003917 | 2025-12-19 |  | 705891.15
V6004041 | 2026-01-23 |  | 779456.97
V6004091 | 2026-02-13 |  | 825957.45
V6004189 | 2026-03-19 |  | 459566.1
V7004291 | 2026-04-03 |  | 15524
V7004396 | 2026-05-01 |  | 654507.9
27-00181 | 2026-05-15 |  | 770876.55
27-00002 | 2026-05-30 |  | 510082.2
27-00328 | 2026-07-01 |  | 548194.5
| 2026-08-31 |  | 73962.9 | Received in October, not in financials
|  | Grand Total: | 8065185.02

## GMB
P.O. No. | Order Date Description |  | P.O. Total
V4000087 | 2023-04-19 |  | 3661.82
V4000198 | 2023-05-19 |  | 8516.25
V4000306 | 2023-06-16 |  | 4793.71
V4000415 | 2023-07-14 |  | 8994.14
V4000537 | 2023-08-24 |  | 2601.25
V4000647 | 2023-09-22 |  | 9968.13
V4000670 | 2023-09-29 |  | 1633.75
V4000743 | 2023-10-20 |  | 11103
V4000771 | 2023-10-27 |  | 8325.28
V4000828 | 2023-11-17 |  | 21282.75
V4000921 | 2023-12-22 |  | 49387.91
V4000995 | 2024-01-19 |  | 24590.48
V4001020 | 2024-01-26 |  | 4731.62
V4001114 | 2024-02-23 |  | 19364.22
V4001172 | 2024-03-15 |  | 21004.95
V5001538 | 2024-05-10 |  | 67821.09
V5001678 | 2024-06-21 |  | 33719.13
V5001789 | 2024-07-19 |  | 37054.62
V5001897 | 2024-08-16 |  | 12592.95
V5001926 | 2024-08-23 |  | 5266.25
V5002028 | 2024-10-01 |  | 10109.75
V5002118 | 2024-10-18 |  | 6706.25
V5002184 | 2024-11-15 |  | 9888.31
V5002215 | 2024-12-02 |  | 5268.2
V5002263 | 2024-12-20 |  | 9689.81
V5002329 | 2025-01-17 |  | 14785.8
V5002388 | 2025-02-21 |  | 803.75
V5002756 | 2025-03-28 |  | 14808.37
V6002830 | 2025-04-14 |  | 6202.5
V6003056 | 2025-04-25 |  | 1043.75
V6003120 | 2025-05-09 |  | 21692.49
V6003146 | 2025-05-19 |  | 31150.04
V6003172 | 2025-05-30 |  | 1150
V6003435 | 2025-08-01 |  | 3966.26
V6003514 | 2025-08-22 |  | 12678.75
V6003595 | 2025-09-12 |  | 4526.25
V6003701 | 2025-10-10 |  | 4331.25
V6003824 | 2025-11-21 |  | 7865.55
V6003919 | 2025-12-19 |  | 7613.75
V6004010 | 2026-01-16 |  | 5009.38
V6004093 | 2026-02-13 |  | 5666.25
V6004109 | 2026-02-20 |  | 859
V6004192 | 2026-03-19 |  | 1140.5
V7004271 | 2026-04-01 |  | 6791.25
V7004319 | 2026-04-10 |  | 5551
V7004369 | 2026-04-24 |  | 403.25
27-00137 | 2026-05-14 |  | 1961.5
27-00024 | 2026-05-31 |  | 8942.25
27-00188 | 2026-06-04 |  | 6317.25
27-00540 | 2026-08-10 |  | 5095
27-00511 | 2026-09-04 |  | 3966.88
27-00511 | 2026-07-06 |  | 3117.75
|  | Grand Total: | 573335.76

## Interest
Date | Ref/Check | Description | Amount
2025-03-31 |  | INTEREST PAYMENT | 2896.56
2025-04-30 |  | INTEREST PAYMENT | 7861.95
2025-05-31 |  | INTEREST PAYMENT | 8151.23
2025-06-30 |  | INTEREST PAYMENT | 10162.11
2025-07-31 |  | INTEREST PAYMENT | 13201.21
2025-08-31 |  | INTEREST PAYMENT | 13246.58
2025-09-30 |  | INTEREST PAYMENT | 12781.63
2025-10-31 |  | INTEREST PAYMENT | 12834.28
2025-11-30 |  | INTEREST PAYMENT | 12460.29
2025-12-31 |  | INTEREST PAYMENT | 6681.08
2026-01-30 |  | INTEREST PAYMENT | 4294.23
2026-02-27 |  | INTEREST PAYMENT | 3349.17
2026-03-31 |  | INTEREST PAYMENT | 4857.38
2026-04-30 |  | INTEREST PAYMENT | 5259.48
2026-05-29 |  | INTEREST PAYMENT | 9242.65
2026-06-30 |  | INTEREST PAYMENT | 14845.54
2026-07-31 |  | INTEREST PAYMENT | 15389.86
2026-08-31 |  | INTEREST PAYMENT | 15440.17
2026-09-30 |  | INTEREST PAYMENT | 14899.63
2026-10-31
2026-11-30
2026-12-31
2027-01-31
2027-02-28
2027-03-31
187855.03